## 00_Test_Plan
Topic | Details
Project Name | SauceDemo E-Commerce Website
Website | https://www.saucedemo.com/
Testing Objective | To verify that the major features of the application work as expected and meet the defined requirements.
Testing Scope | Login, Products, Product Sorting, Cart, Checkout, Logout
Testing Types | Functional Testing, UI Testing, Positive Testing, Negative Testing, Smoke Testing, Regression Testing
Test Environment | Windows 11, Google Chrome
Test Data | Username: standard_user, Password: secret_sauce
Entry Criteria | Application is accessible, Login page is available, Test environment is ready
Exit Criteria | Planned test cases are executed, failed test cases are retested, major defects are documented
Out of Scope | Performance Testing, Security Testing, Real Payment Gateway Testing
Deliverables | Test Plan, Test Scenarios, Test Cases, Test Execution Results, Bug Reports, Test Summary
Tester | Ayesha

## 01_Test_Scenarios
Scenario ID | Module | Test Scenario Description | Priority | Number of Test Cases
TS-001 | LOGIN | Validate the working of login functionality | High | 6
TS-002 | PRODUCTS | Validate the working of product functionality | Medium | 3
TS-003 | CART | Validate the working of 'add to cart' functionality | Medium | 3
TS-004 | CHECKOUT | Validate the working of checkout functionality | Medium | 3
TS-005 | LOGOUT | Validate the working of logout functionality | High | 1

## 02_Login
Test Case ID | Test Scenerio | Test Cases | Preconditions | Test Steps | Test Data | Expected Result | Actual Result | Status | Priority
TC-LOGIN-001 | TS-001 LOGIN Functionality | Verify login with valid credentials | User is on the SauceDemo Login page. | 1. Enter valid username. 2. Enter valid password. 3. Click Login. | Username: standard_user Password: secret_sauce | User should log in successfully and navigate to the product page | User successfully logged in and navigated to the Products page. | pass | High
TC-LOGIN-002 | TS-001 LOGIN Functionality | Verify login with invalid username | User is on the Login page. | 1. Enter invalid username. 2. Enter valid password. 3. Click Login. | Username: invalid_user Password: secret_sauce | User should not log in successfully and an appropriate error message should be displayed | The login attempt was rejected and a common error message indicating that the username and password did not match was displayed. | pass | High
TC-LOGIN-003 | TS-001 LOGIN Functionality | Verify login with invalid password | User is on the Login page. | 1. Enter valid username. 2. Enter invalid password. 3. Click Login. | Username: standard_user Password: Invalid_password | User should not log in successfully and an appropriate error message should be displayed | The login attempt was rejected and a common error message indicating that the username and password did not match was displayed. | pass | High
TC-LOGIN-004 | TS-001 LOGIN Functionality | Verify login with empty username | User is on the Login page. | 1. Leave username field empty. 2. Enter valid password. 3. Click Login. | Username: empty Password: secret_sauce | User should not log in successfully and an appropriate error message should be displayed | The login attempt was rejected and a validation message indicating that the username is required was displayed. | pass | Medium
TC-LOGIN-005 | TS-001 LOGIN Functionality | Verify login with empty password | User is on the Login page. | 1. Enter valid username. 2. Leave password field empty. 3. Click Login. | Username: standard_user Password: empty | User should not log in successfully and an appropriate error message should be displayed | The login attempt was rejected and a validation message indicating that the password is required was displayed. | pass | Medium
TC-LOGIN-006 | TS-001 LOGIN Functionality | verify login with both fields empty | User is on the Login page. | 1. Leave username field empty. 2. Leave password field empty. 3. Click Login. | Username: empty Password: empty | User should not log in successfully and an appropriate error message should be displayed | The login attempt was rejected and a validation message indicating that the username is required was displayed. | pass | Medium

## 03_Products
Test Case ID | Test Scenerio | Test Cases | Preconditions | Test Steps | Test Data | Expected Result | Actual Result | Status | Priority
TC-PRODUCT-001 | TS-002 PRODUCT Functionality | Verify products are displayed | User is successfully logged in. | 1. Login with valid credentials. 2. Observe the Products page. | Username: standard_user Password: secret_sauce | Products should be displayed with product name, image and price. | The products were displayed successfully with their respective product names, images, and prices. | Pass | High
TC-PRODUCT-002 | TS-002 PRODUCT Functionality | Verify product information | User is on Products page. | 1. Select any product. 2. Observe product name. 3. Observe product image. 4. Observe product price. 5. Observe product description. | Any available product | Product information should be displayed correctly. | The selected product information, including product name, image, price, and description, was displayed correctly. | Pass | Medium
TC-PRODUCT-003 | TS-002 PRODUCT Functionality | Verify product sorting | User is on Products page. | 1. Open the sorting dropdown. 2. Select a sorting option. 3. Observe the product list. | Available sorting options | Products should be displayed according to the selected sorting option. | The products were successfully sorted according to the selected sorting op | Pass | Medium

## 04_Cart
Test Case ID | Test Scenerio | Test Cases | Preconditions | Test Steps | Test Data | Expected Result | Actual Result | Status | Priority
TC-CART-001 | TS-003 CART Functionality | Verify user can add product to cart | User is on Products page. | 1. Select any product. 2. Click Add to Cart. 3. Open the Cart. | Any available product | Selected product should be added to the cart. | The selected product was successfully added to the cart and was displayed in the cart. | pass | High
TC-CART-002 | TS-003 CART Functionality | Verify user can remove product to cart | User is on Products page. | 1. Select any product. 2. Click Add to Cart. 3. Remove the Cart. | Any available product | Selected product should be remove from the cart. | The selected product was successfully removed from the cart and was no longer displayed. | pass | High
TC-CART-003 | TS-003 CART Functionality | Verify cart item count | User is on Products page. | 1. Add one product to cart. 2. Observe cart icon. 3. Add another product. 4. Observe cart icon again. | Two available products | Cart item count should update correctly according to the number of added products. | The cart item count was updated correctly when products were added to the cart. | pass | Medium

## 05_Checkout
Test Case ID | Test Scenerio | Test Cases | Preconditions | Test Steps | Test Data | Expected Result | Actual Result | Status | Priority
TC-CHECKOUT-001 | TS-004 CHECKOUT Functionality | Verify checkout with valid information | User is logged in and has at least one product in the cart. | 1. Open Cart. 2. Click Checkout. 3. Enter First Name. 4. Enter Last Name. 5. Enter Postal Code. 6. Click Continue. | First Name: Ayesha Last Name: Siddika Postal Code: 1207 | User should proceed to the Checkout Overview page. | The Checkout option was not available, so the checkout process could not be initiated. | Blocked | High
TC-CHECKOUT-002 | TS-004 CHECKOUT Functionality | Verify mandatory checkout fields | User is on Checkout Information page. | 1. Leave required fields empty. 2. Click Continue. 3. Observe the validation message. | Empty required fields | User should not proceed and appropriate validation message should be displayed. | The Checkout option was not available, so the checkout information page could not be accessed and mandatory field validation could not be tested. | Blocked | High
TC-CHECKOUT-003 | TS-004 CHECKOUT Functionality | Verify order completion | User has added a product and entered valid checkout information. | 1. Proceed to Checkout Overview. 2. Review order information. 3. Click Finish. 4. Observe the confirmation page. | Valid checkout information | Order should be successfully completed and confirmation message should be displayed. | The Checkout option was not available, so the order completion process could not be tested. | Blocked | High

## 06_logout
Test Case ID | Test Scenerio | Test Cases | Preconditions | Test Steps | Test Data | Expected Result | Actual Result | Status | Priority
TC-LOGOUT-016 | TS-005 LOGOUT Functionality | Verify logout functionality | User is successfully logged in. | 1. Open the navigation menu. 2. Click Logout. 3. Observe the page. | Username: standard_user Password: secret_sauce | User should be logged out and redirected to the Login page. | The user was successfully logged out and redirected to the Login page. | Pass | High

## 07_Test_Execution
Test Case ID | Module | Test Execution Date | Actual Result | Status | Tester | Comments
TC-LOGIN-001 | LOGIN | 2026-09-27 | User successfully logged in and navigated to the Products page. | pass | Ayesha | _
TC-LOGIN-002 | LOGIN | 2026-09-27 | The login attempt was rejected and a common error message indicating that the username and password did not match was displayed. | pass | Ayesha | _
TC-LOGIN-003 | LOGIN | 2026-09-27 | The login attempt was rejected and a common error message indicating that the username and password did not match was displayed. | pass | Ayesha | _
TC-LOGIN-004 | LOGIN | 2026-09-27 | The login attempt was rejected and a validation message indicating that the username is required was displayed. | pass | Ayesha | _
TC-LOGIN-005 | LOGIN | 2026-09-27 | The login attempt was rejected and a validation message indicating that the password is required was displayed. | pass | Ayesha | _
TC-LOGIN-006 | LOGIN | 2026-09-27 | The login attempt was rejected and a validation message indicating that the username is required was displayed. | pass | Ayesha | _
TC-PRODUCT-007 | PRODUCTS | 2026-09-27 | The products were displayed successfully with their respective product names, images, and prices. | pass | Ayesha | _
TC-PRODUCT-008 | PRODUCTS | 2026-09-27 | The selected product information, including product name, image, price, and description, was displayed correctly. | pass | Ayesha | _
TC-PRODUCT-009 | PRODUCTS | 2026-09-27 | The products were successfully sorted according to the selected sorting op | pass | Ayesha | _
TC-CART-010 | CART | 2026-09-27 | The selected product was successfully added to the cart and was displayed in the cart. | pass | Ayesha | _
TC-CART-011 | CART | 2026-09-27 | The selected product was successfully removed from the cart and was no longer displayed. | pass | Ayesha | _
TC-CART-012 | CART | 2026-09-27 | The cart item count was updated correctly when products were added to the cart. | pass | Ayesha | _
TC-CHECKOUT-013 | CHECKOUT | 2026-09-27 | The Checkout option was not available, so the checkout process could not be initiated. | Block | Ayesha | Checkout option unavailable
TC-CHECKOUT-014 | CHECKOUT | 2026-09-27 | The Checkout option was not available, so the checkout information page could not be accessed and mandatory field validation could not be tested. | Block | Ayesha | Checkout option unavailable
TC-CHECKOUT-015 | CHECKOUT | 2026-09-27 | The Checkout option was not available, so the order completion process could not be tested. | Block | Ayesha | Checkout option unavailable
TC-LOGOUT-016 | LOGOUT | 2026-09-27 | The user was successfully logged out and redirected to the Login page. | pass | Ayesha | _

## 08_Bug_Tracking
Bug ID | Test Case ID | Module | Bug Title | Steps to Reproduce | Expected Result | Actual Result | Severity | Priority | Status

## 09_Test_Summary
Metric | Result
Project Name | SauceDemo E-Commerce Website
Total Test Cases | 16
Executed Test Cases | 13
Passed Test Cases | 13
Failed Test Cases | 0
Blocked Test Cases | 3
Not Executed Test Cases | 0
Total Bugs Found | 0
Critical Bugs | 0
High Severity Bugs | 0
Medium Severity Bugs | 0
Low Severity Bugs | 0
Retested Cases | 0
Regression Testing Status | Not started
Overall Testing Status | Partially Completed
Testing Conclusion | 13 test cases were executed and passed successfully. 3 checkout test cases were blocked because the Checkout option was not available during testing.

## 10_RTM
Requirement ID | Requirement | Source | Test Case ID | Status
REQ-001 | User should be able to log in using valid credentials. | Application Functional Requirement | TC-LOGIN-001 | PASS
REQ-002 | System should reject invalid login credentials. | Application Functional Requirement | TC-LOGIN-002, TC-LOGIN-003 | PASS
REQ-003 | System should validate required login fields. | Application Functional Requirement | TC-LOGIN-004, TC-LOGIN-005, TC-LOGIN-006 | PASS
REQ-004 | System should display available products with relevant information. | Application Functional Requirement | TC-PRODUCT-001 | PASS
REQ-005 | User should be able to view product details. | Application Functional Requirement | TC-PRODUCT-002 | PASS
REQ-006 | User should be able to sort products using the available sorting options. | Application Functional Requirement | TC-PRODUCT-003 | PASS
REQ-007 | User should be able to add a product to the cart. | Application Functional Requirement | TC-CART-001 | PASS
REQ-008 | User should be able to remove a product from the cart. | Application Functional Requirement | TC-CART-002 | PASS
REQ-009 | Cart item count should update when products are added. | Application Functional Requirement | TC-CART-003 | PASS
REQ-010 | User should be able to initiate checkout with products in the cart. | Application Functional Requirement | TC-CHECKOUT-001 | BLOCKED
REQ-011 | Checkout should require the necessary customer information. | Application Functional Requirement | TC-CHECKOUT-002 | BLOCKED
REQ-012 | User should be able to complete an order after providing valid checkout information. | Application Functional Requirement | TC-CHECKOUT-003 | BLOCKED
REQ-013 | Authenticated user should be able to log out and return to the login page. | Application Functional Requirement | TC-LOGOUT-001 | PASS